Bardsey Neighbourhood Plan Steering Committee

Minutes of the Meeting held on 17.2.16

Present :- Lyndsay Burns (LB),. Ian Frankland (IF), June Gallant (JG). Chris Sidle (CS), Ed Stentiford (ES) and Martin Ward (MW).

Apologies: Jane Ambrose, Mike Bosomworth, Jane Ingham, and Stephen Bucknell. .

.                                                           Declarations of any Pecuniary and Other Interests  None.

Minutes of Meeting held on .20.1.16  These were approved.

.Matters Arising :-

1..Visit to Ian McKay by IF and CS –  CS reported that this had been a very constructive meeting at which the they had spent almost a whole  morning with IM going through the entire revised draft consultation document.  They had also consulted him on the proposed Project Plan drawn up by IF. IM had  made a number of recommendations in the light of the latest knowledge and practice in Neighbourhood Planning, as well as wider planning regulations.  CS has now e mailed members the new version of our latest vision, objectives and policies, highlighting possible revisions proposed by IM, and where possible  including  reasons for these ,and IF has e mailed the revised Project Plan .

CS  informed the SC of certain general considerations arising from their discussion.

- Linton NDP Plan – A SHLAA  site owner had raised a legal objection which was taken to a Judge, who ruled in favour of the Linton NDP Group. IM said this was encouraging. LCC has, however, changed its position  slightly as a result. They now require 6 weeks notice of a referendum in order to deal with any potential challenge before any referendum.

- At the National level advice has recently been received from Historic England about the necessity for conducting an Environmental Sustainability Assessment . IM had previously been against this, on the grounds that Collingham had not been required to undertake one. LCC is now considering a sensible accommodation.

- Sustainability Assessment - This is an optional extra. IM advises in favour.

- Clarification on status regarding consultation – IF and CS had been hopeful that, given the level of previous consultation, the SC would not need to carry out a further round of consultation . IM, however, said that this would be required, but could be a relatively simple procedure. Letters would have to be sent to all residents advising them of the option of responding to the Revised Draft Consultation  document. Hard copies of this would be distributed in strategic places in the village and could also be viewed on line.

- Need to concentrate more on obtaining responses from Statutory Consultees.

IF then discussed proposed changes to the PPP based on discussion at the last SC meeting and the meeting  with IM. He had e mailed Revision 2 to all members prior to the meeting. IM had suggested that May 2017 would be a likely date for the Referendum. IF had, however,  tried to plot an intermediate route between this and his original proposed date , and would now like to see the Referendum date brought forward to February 2017, with completion by April 2017. He is keen to keep pressure on LCC to make this possible. IF then proceeded to outline the dates for each remaining  stage from the present to April 2017.

The possibility of a Drop In Session was discussed. This might occur across 2 days, commencing with the day of the Annual Meeting (likely to be April 28th) at which a presentation would be made, and with a second session the following Saturday . Presentation boards showing photos depicting policies and simple accompanying text would be set out  round the Village Hall.

The need for a Proof Reader was also discussed. SB had e mailed his willingness to contact a retired lady who had in the past worked for Roal Dahl . The SC welcomed this.

The SC can appoint its own examiner. IF is keen to use Nigel MC Gurk when the time comes .

CS then took the SC through the Revised NDP document , noting and explaining where possible, the changes suggested by IM. Each of these was considered, and with a few minor alterations, agreed on. CS will now incorporate all the changes in a revised document.  (Action CS) .

2. Boundary Change for Bardsey NDP   CS has responded to the e mail from Steve Wilkinson and has  requested  that the NDP boundary should now follow the new political boundary of Bardsey. He provided the reason and supplied a current map of Bardsey. JG is to contact Steve Wilkinson about a response  from Scarcroft who also  have to provide an official request for the boundary change . (Action JG)

3 Update and Review – Actions List , Content  and Progress :

- Measures to protect hedges, fences etc. . This has been done.

- Review of Leeds Local Plan.

- Compilation of Comprehensive list of Scheduled Monuments, Listed Buildings etc.-Completed.

- Map of Community Facilities – Being completed by LB   (Action LB)

- Footpaths, Bridleways and Cycleways.- As above. (Action LB)

- Favourite Viewpoints – List provided by IF for completion by LB (Action LB)

- Wildlife and Ecology – Done.

4. Resources and Needs    ES will work out the likely expenditure on the next Consultation, the Drop In Meeting, and hiring of the Proof Reader. (Action ES)

5..A.O.B     None.

6..Dates of next 2 Meetings  Wednesday March 16 and Wednesday April 20th

BPC St. Co. February 16 Mins