Bardsey Neighbourhood Plan Steering Committee

Minutes of the Meeting held on 18.11.15

Present :- Ed Stentiford(ES), Chris Sidle (CS), Mike Bosomworth (MB), Jane Ingham (JI), Martin Ward (MW)

Apologies:- Ian Frankland , Jane Ambrose, Stephen Bucknell and Lyndsay Burns.

.                                                           Declarations of any Pecuniary and Other Interests. None.

Minutes of Meeting held on 21.10.15  Approved.

Matters Arising :-                                                                                                                            (a)Possible  Path from Keswick Court to Keswick Lane.   There is no definite information on this. The Planning Officer has reported that Park Lane Homes have not applied for any change to clause 11 in the Approval specifying a footpath across the site.

Steering Committee -  resources and needs : -                                                                                  (a) Finance -  The Chairman has learnt that grants up to £8k are available but must be used within 6 months and must be applied for in connection with specific projects. He has not therefore applied for any money to date.                                                                                                                                                                                                       (b) Project timetable – Not yet started.

Letter from BPC re Site Allocations – The Council has written supporting the original SAP   proposals  which include Headley Hall.

Full Report to SC on work undertaken by Sub-Committees on Analysis of Responses from Residents and from Statutory Consultees to Draft NDP Document.   The SC had been circulated prior to the meeting with a full list of all comments received and proposed responses to each, from the various small sub committee which have met during the last month. These were all  approved with no major objections, simply a slight change of wording in some instances. The emphasis on retention of the Green Belt had been  strengthened in line with the strong public support for this. In one section, it was agreed that a further useful  addition  would be  the inclusion of a map (and possibly  photos )of  cherished  views , as included in the Clifford Pre Submission Draft NDP.

Wider Actions Proposed : -

- Footpaths, Cycleways and Bridleways                                                                                        a. Addition of a map of footpaths,cycleways and bridleways to the NDP showing existing facilities and NDP aspirations/ projects – MB reported that he possesses a number of OS maps which could be photocopied.  Jack Cairns had earlier obtained approval for use of OS maps.  It was agreed that the boundary map should show the new Bardsey boundary. These to be included as aspirations.   (Action MB)                                                                                            b. Need to check status of old railway line from Wood Lane to Thorner Lane and if necessary apply to designate it as a footpath and/ or bridleway. MB offered to do this. (Action MB) .

- Environment -                                                                                                                                a.. Add the PC's report on wildlife and ecology to the NDP- ES offered to deal with this (Action ES)                                                                                                                                      b. Establish the scope of the NDP to prescribe measures to protect hedges , fences etc. and if possible further strengthen the drafting policies BE2 and BES. JG will contact David Gluck on this .(Action JG).

- Built Environment and Housing                                                                                                    a. Need to conduct a review of the current Leeds Local Plan in the light of the draft NDP, and identify obvious discrepancies (if any). In this event review references to the Leeds Local Plan in the NDP and determine what further drafting may be appropriate. JG to refer this to David Gluck (Action JG) .                                                                                     b. Compile a comprehensive list of scheduled monuments, listed buildings and conservation areas and add to the NDP. ES reported that he is already in possession of this. (Action ES) .                                                                                                                         c. Clarify the implications of recent changes in planning regulations on the drafting of housing policies (especially H3) and re-draft if necessary.  (Action SB)

- Community Facilities                                                                                                                  a. Approach LCC for confirmation of designated green spaces currently listed in the parish. Review the list,decide if additional listings are required, and if so initiate due process. Agreed to approach David Gluck for information on need to apply and how to go about it. (Action JG) .                                                                                                               b. Compile a map of community facilities, listed green spaces, SSSis, SSHIs etc and add to the NDP.

- General                                                                                                                                               a. Add a formal commitment by the Parish Council to conduct a review of NDP policies every 5 years during the course of its validity. CS offered to do this. (Action CS)                                                                                                                                        b. Add a projects plan to the NDP – this to include the possible establishment of a shop/ cafe/ internet point at the village hall, and the establishment of a public right of way from the Congreves to Keswick Lane. This should be agreed by the full SC

A.O.B   None.

Dates of next 2 Meetings :- Wednesday December 17th and Wednesday January 20th

BPC St. Co. November 15 Mins.