Bardsey Neighbourhood Plan Steering Committee

Minutes of the Meeting held on 20.1.16.

Present : Jane Ambrose, (JA), Stephen Bucknell (SB), Lyndsay Burns, (LB),Ian Frankland (IF), June Gallant (JG), Jane Ingham (JI), Chris Sidle (CS), and Ed Stentiford (ES).

Apologies: .Mike Bosomworth and Martin Ward.

.                                                           Declarations of any Pecuniary and Other Interests ES declared an interest in land he owns  at Spear Fir which could potentially become a brown field site.

Minutes of Meeting held on .16.12.15.   These were approved.

Matters Arising :   Whilst  it was agreed at the November Meeting that MW would oversee completion of the NDP, in his absence IF  has populated the Project Plan The following outstanding items were reviewed for action.

1. Update and Review – Actions List, Content and Progress:

- Measures to protect hedges, fences etc.- Agreed to ask David Gluck for help on strengthening policies BE2 and BE3.  (Action JG)

- Review of Leeds Local Plan - No action planned.

- Compilation of Comprehensive list of Scheduled Monuments, Listed Buildings -

ES has produced a map of historic sites and a list of Listed Buildings.

- Green Spaces- ES has completed this list.

- Map of Community Facilities, Listed Green Spaces, SSSIs, SSHIs. - Partly done. Some uncertainty over presentation.

- Footpaths, Bridleways and Cycleways. MB (currently on holiday) had agreed to provide this. JG offered to obtain a map and description of paths from ROW, and LB will obtain information from the Ordnance Survey and produce a map to include aspirational paths .It is necessary to check whether we still have Crown copyright. JG to check with Jack Cairns. (Action JG /LB)

Status of old Railway Line from Wood Lane to Thorner Lane – Seek information

from ROW. (Action JG)     .

- Favourite Viewpoints – LB will take these from Ordnance Survey and VDS and CS will photograph those preferred.  (Action LB/ CS)

- Report on Wildlife and Ecology - This completed and to be included in appendix.

- Clarification implications of Recent Changes in Planning Regulations on drafting of Housing Policies (especially H3) and Re-draft if necessary. - Suggest asking David Gluck to help with this.(Action JG)

Project Plan –  The SC reviewed the next stages to the  Final Draft of the NDP being issued to LCC.  The SC agreed that completion of the revised draft NDP could not be achieved by the end of January. Further work required will be the Sustainability Assessment and Habitats Report (unless waived officially by a Screening Opinion from Leeds City Council, which the SG has been advised off the record is very probable, but which has not yet been provided by Ian Mackay).  CS needs to check again with IM. It is also desirable to find suitable proof readers before final submission of the document.  It was agreed to aim at the end of February to complete the outstanding actions. IF hoped the whole NDP would be completed by November 31 2016. It was also noted that no official confirmation has yet been received from LCC (Steve Wilkinson) that the boundary of the Bardsey NDP area has been amended to bring it into line with the new Parish Boundary.  (Action CS)

Consultation Statement: - IF has   has researched the Conditions Statement provided by the 'designated front runner' NDPs and has established the importance of providing a comprehensive list of all approaches made to the village for their views – public meetings, questionnaires, newsletter reports, website reports etc. Following from this, should be listed the SC reaction, then steps taken to achieve each approved action.                                                                                                              He listed a large number of official groups and organisations not  already consulted.                                                                                       There is uncertainty over whether it is necessary to go through a further village consultation process (advice from IM).                                                                                                               David Gluck will be asked to draw up the Basic  Conditions Statement for presentation to LCC (Action JG/CS/ES).

Consultation from Dept. of Local Government on Proposed Changes to Planning Regulations. BPC had taken the decision that if a Council response was required ( as opposed to individual responses) this should be sent from the SC. It was agreed that this is not required. It relates to National Planning Policy and is not necessarily relevant to Bardsey. The response from this one small village is unlikely to make any difference. Any changes are unlikely to be implemented before our NDP is completed. Bardsey PC has already committed to a generic approach to development and cannot at this stage consult the village once again about changing course.

A.O.B.                                                                                                                                             (a) CS asked whether all the comments, responses from the SC, and actions taken subsequently by them should be shown on the NDP website in detail or in summary. There was some discussion on  but it was eventually agreed that in order to leave no stone unturned in showing the Examiner the degree of communication with the village, it should all be shown in full detail on the website.                                                                                                                                      (b) LB reported that Thorp Arch have withdrawn their application for the time being.

Dates of next 2 meetings: -                                                                                                   Wednesday February 17                                                                                                               Wednesday March 16.

BPC St. Co. January 16 Mins.